## Sheet1
PRODUCT BACKLOG
Topic | User Story | Tasks | Story Points | Definition of Done | CONVERSATION | I | Independant
Questionnaire | As a member of staff, I want to be able to create questionnaires via the system, so that I don’t need to use external systems | Design and create database (questionnaire: title, questions, answers): - Create ER diagram - Normalise - Create database - Add data Design and create website: - Desgin pages (website template, create questionnaire page) - Create pages (website template, create questionnaire page) Java script and php, questionaire logic: - Connect to the database - Create a new questionnaire - Add questions | 55 | -The website should look professional and the design should be approved by the stake holders -The website should have university branding -The text design should satifsy WCAG 2.0 AA -The created questionaire should be saved in a database -The database should at least satisfy 3NF -The website has an ability to create and store a questionaire -The creator should be easy and intuitive to use approved by the stake holders -The website should be able to send the questionaire to be stored in the database | - the website design should be clean and consistent - the wesite could follow the universitie's generic guidelines and more specific guidelines relating to what they use ( https://uod-web-services.gitlab.io/uod-website/pattern-library/ https://www.dundee.ac.uk/brand/ ) - The number of questions in a questionnaire can vary from 2-3 questions to around 100 | N | Negotiable
Questionnaire | As a member of staff, I want to be able to delete questionnaires I created, so that they can be managed better |  | 5 | - members of staff can deleted existing questionnaires |  | V | Valuable
Questionnaire | As a member of staff, I want to be able to edit questionnaires I created, so that they can be managed better |  | 8 | - members of staff can edit existing questionnaires | - The ability to edit questionnaires is important, users will likely want to edit them between their creation and them being released - "There are times where we do pilot studies, check that things are working properly, and then release a V2" | E | Estimable
Questionnaire | As a member of staff, I NEED to be able to export results from the questionnaires to CSV files, so that I can impot them into our data analysis software |  | 8 | -All answers to the questionaires should be able to be exported to a CSV file. |  | S | Small
Questionnaire | As a member of staff, I want to be able to see simple charts visualising the data, so that I can see roughly how things are looking |  | 21 | - Charts can be created from existing data - Charts can be viewed by members of staff uppon request | - Simple charts visualising numerical data | T | Testable
Questionnaire | As a member of staff, I want the system to look professional (as deemed by the clients), so that the data it consistent |  | 13 | - Design is clean and consistent - Designs could follow university graphic design guidelines
Questionnaire | As a member of staff, I want the system to have university branding, so that the system conforms to university standards |  | 5 | - All website pages include university branding
Questionnaire | As a participant, I want the questionnaires to be easy to use, so that I can complete them correctly and efficiently |  | 5 | - Web pages are intuitive, easy to navigate - all page functionalities (buttons and input fields) are labled appropriately | - needs to comply with WCAG 2.0 AA | S | Specific
Questionnaire | As a lab manager, I want to be able edit account details so that I can change their role and other detials |  | 13 | - Participants are able to find and access questionnaires - Participants are able to complete questionnaires - Questionnair results are stored apporpriately in the database
Questionnaire | As a member of staff, I want questionnaires to have options for text answers, so that I can gauge responses accurately | Design and add to database: - store text answers, user ID Design and create: - text input option when creating a questionnaire - participant questionnaire answer page Java script and php, questionaire logic: send questionnaire results to be stored in the database | 5 | - When creating a question for a questionnaire, staff are able to select input type "text" - appropriate functionality is added to the questionnaire | - must have functionality | M | Measurable
Questionnaire | As a member of staff, I want questionnaires to have options for multiple choice answers, so that I can gauge responses accurately | Design and add to database: - store multiple choice answers, user ID Design and create: - multiple choice input option when creating a questionnaire Java script and php, questionaire logic: send questionnaire results to be stored in the database | 5 | - When creating a question for a questionnaire, staff are able to select input type "multiple choice" - appropriate functionality is added to the questionnaire | - must have functionality
Questionnaire | As a member of staff, I want questionnaires to have options for Likert Scored answers, so that I can gauge responses accurately |  | 3 | - When creating a question for a questionnaire, staff are able to select input type "Likert Scored" - appropriate functionality is added to the questionnaire | - must have functionality
Video | As a member of staff, I want a transcript to be generated automatically so that I don't need to create it manually |  | 55 | - The transcript is generated and is at least 80% accurate |  | A | Achievable
Video | As a member of staff, I want to be able to watch 2 or 3 videos at the same time so that i can compare them |  | 21 | - All videos play on the users screen |  | R | Relevant
Video | As a member of staff, I want basic video control that controls all videos at the same time so that I have synchronous control over all the videos |  | 21 | - users are able to pause, play and rewind all currently displayed video footage at the same time
Video | As a member of staff, I want basic video control that controls an individual video, so that I can control video playback individually |  | 13 | - users are able to pause, play and rewind individual videos
Video | As a member of staff, I want the ability to identify quotes from the generated transcripted so that I can use them easily in papers. |  | 21 | - users can select a section of the transcript and add it to a list of quotes - quotes and all relevant information are stored in the database - users have access to a list of their quotes
Video | As a member of staff, I want the ability to attach tags to quotes so that I can search them easily |  | 8 | - users can create new tags - users can add tags to existing quotes | - Tags are core functionality - researchers tag all quotes, then look at how many of each tag is present to use for analysis
Video | As a member of staff, I want to be able to add relationships between quotes and denote these by giving them a super theme tag, so that I can find similar quotes easily |  | 5 | - users can create new super tags - users can add super tags to existing quotes
Video | As a memeber of staff, I can upload videos to the system, so that I can use the system to analyse them |  | 55 | - users can select and upload videos to the system - videos are stored in the database - videos can be viewed via the system in an appropriate environment for analysis
Video - timestamps | As a member of staff, I want the ability to add timestamps while watching a video so that I can keep track of anything interesting that happens |  | 21 | - users can select a "create timestamp at current time" button to create a timestamp at the current time while viewing videos - timestamps should be stored in the database
Video - timestamps | As a member of staff, I want the ability to add comments to timestamps so that I know what the timestamp is refering to |  | 13 | - users can select an existing timestamp and add a text input saved as a comment - comments are stored in the database with all the relevant information
Video - timestamps | As a member of staff, I want the ability to edit comments on timestamps so that I more control of the information within them |  | 5 | - users can select an existing comment and edit it's value
Video - timestamps | As a a member of staff, I want the ability to be able to view all the timestamps with comments that I have made so that I can refer to them later |  | 8 | - users can view all of their existing timestamps - users can view existing comments corresponding to timestamps displayed
Login | As a user of the program, I want to be able to login so that I can access my information easily | Design and add to database (login: username, real name, password, role, access rights): - Add to ER diagram - Normalise - Add to database - Add data Design and create pages: - login page - dashboard Java script and php, questionaire logic: - Check login details against stored data, return appropriate result | 55 | - users are able to log into their existing account
Login | As a user of the program, I want to be able to see what "role" I've logged into so that I know I am accessing the relevant information |  | 8 | - the user's role is visable on the dashboard
Login | As a user of the program, I want access to a dashboard so that I can see and access the functionalities of the program I have access to |  | 13 | - users are able to access their dashboard
Accessability | As a user of the program, I want the program to work on whatever monitor size I have so that I can see all the buttons I need to access |  | 13 | - all buttons are visible on monitor sizes 1080x720, 1920x1080
Accessability | As a user of the program, I want the ability to change the font size so that I can read the text easier |  | 13 | - users can chose between 3 different font sizes
Ethics | As a member of staff, I need to ensure that participants have agreed to our privacy policy before they start the questionnaire, so the participant understand how are were going to use their data and that we don't violate the Data protection act and GDPR | Research, design and create page: - Collect privacy policy - design page - create page Add to database: - user accepted/rejected Add accept/reject functionality | 13 | - participants can view and respond to privacy policy agreement forms - user responces are stored in the database appropriately - staff can view responces
Ethics | As a member of staff, I need to ensure that participants have agreed to the UoD Ethics before they start the questionnaire, so that we don't violate the user privacy | Research, design and create page: - Collect privacy policy - design page - create page Add to database: - user accepted/rejected Add accept/reject functionality | 2 | - participants can view and respond to privacy policy agreement forms - user responces are stored in the database appropriately - staff can view responces
Ethics | As a participant. I want the ability to check the T&Cs and UOD Ethics before participating in the questionnaire so that I know information about myself is being used correctly |  | 2 | - participants can view and respond to privacy policy agreement forms - user responces are stored in the database appropriately - staff can view responces
Roles | As a lab manager, I want to be able to create accounts so that new people can access the system | Create a stored procedure for adding a new user to the database Design and create page: - lab manager, create new user Java script and php, questionaire logic: link database and html login functionality | 13 | - lab managers are able to add new users to the database - new entries contain all relevant information
Roles | As a user of the program, I want to be able to create an account so that I can access the system |  | 13 | - users are able to add a new user to the database - new entries contain all relevant information
Roles | As a lab manager, I want to be able to reset the passwords of accounts so that users who have forgotten their passwords can gain access |  | 13 | - lab managers are able to select a user and replace the corresponding password value with the default value "password"
Roles | As a lab manager, I want to be able to delete accounts so that people don't have access to things that shouldn't |  | 5 | - lab managers can remove users from the database - all relevant information in the database is also deleted
Roles | As a lab manager, I want to be able to give other accounts different roles so that people can access what they need to |  | 5 | - lab managers can select accounts and select a new role - relevant data is updated in the database
Roles | As a PR (principal researcher) i should have full access to my own experiments so that I can access my work |  | 13 | - PR's can access all the relevant information relating to their experiments - PR's can access tools for analysis for their experiments
Roles | As a principle researcher, I can decide who has access to the experiments I have created, so that I can restrict access |  | 13 | - only users that have been given permission can access others experiments